ANNEXURE – A

PAYMENT SCHEDULE

This Annexure-A forms an integral part of the Plot Sale & Prefabricated Cottage Construction Agreement executed between ADH Associates ("Seller") and Mr. Inayat Ullah Khan ("Purchaser") for the purchase of one (01) Four (4) Marla Residential Plot of plot 107 and one (01) Four (4) Marla Prefabricated Cottage on plot 136 in Smart Valley Murree.

A. CONTRACT VALUE

| Description | Amount (PKR) |
| --- | --- |
| Sale Price of 4 Marla Plot (Plot 107) | 1,200,000/- |
| Construction Price of Prefabricated Cottage (Plot 136) | 4,500,000/- |
| Total Contract Value | 5,700,000/- |

B. PLOT PAYMENT

| Description | Amount (PKR) |
| --- | --- |
| Plot Payment payable at the time of Farad/Inteqal (Transfer of plot 107) | 1,200,000/- |

C. COTTAGE PAYMENT

| Description | Amount (PKR) |
| --- | --- |
| Down Payment payable upon Plot Transfer (Plot 136) | 1,200,000/- |
| Remaining Balance payable through Construction Milestones (Plot 136) | 3,300,000/- |

D. CONSTRUCTION MILESTONE PAYMENT SCHEDULE

| Stage | Construction Activity on plot 136 | % of Cottage Balance | Amount (PKR) |
| --- | --- | --- | --- |
| 1 | Booking / Design Approval / Site Allocation | 10% | 330,000/- |
| 2 | Site Mobilization, Excavation, Layout & Material Mobilization | 10% | 330,000/- |
| 3 | Foundation, PCC, Footings & Plinth Beam | 15% | 495,000/- |
| 4 | Main Steel Frame & Roof Structure | 20% | 660,000/- |
| 5 | Roofing Sheets, Insulation & Waterproofing | 10% | 330,000/- |
| 6 | External Cladding, Double Glazing, Doors & Windows | 10% | 330,000/- |
| 7 | Complete Electrical & Plumbing (MEP Installation) | 8% | 264,000/- |
| 8 | Flooring, Ceiling, Kitchen, Bathroom & Painting Works | 10% | 330,000/- |
| 9 | Wooden Deck, Railings & External Landscaping | 4% | 132,000/- |
| 10 | Testing, Cleaning, Final Inspection & Handover | 3% | 99,000/- |
|  | TOTAL | 100% | 3,300,000/- |

E. PAYMENT CONDITIONS

- The Plot Sale Price of PKR 1,200,000/- shall be paid at the time of Farad/Inteqal (Transfer of plot 107).

- The Cottage Down Payment of PKR 1,200,000/- shall be paid simultaneously with the transfer of the Plot 136

- The remaining PKR 3,300,000/- shall be payable strictly upon completion of each construction milestone as certified by ADH Associates.

- ADH Associates shall issue an Official Receipt for every payment received.

- The Seller reserves the right to suspend construction if any milestone payment remains unpaid until the outstanding amount is cleared.

- The Construction Period shall automatically stand extended for the duration of any delay in payment by the Purchaser.

- Development Charges, utility connection charges, government taxes, duties, stamp duties, registration charges and other statutory charges are not included in the above Contract Price and shall be payable separately by the Purchaser as and when demanded by ADH Associates or the relevant authority.

Accepted and Agreed

| Seller (ADH Associates) | Purchaser |
| --- | --- |
| Authorized Signatory: __________________ | Mr. Inayat Ullah Khan |
| Signature: _____________________________ | Signature: __________________ |
| Date: _________________________________ | Date: __________________ |